## AE Invoice
STANDARD INVOICE FORM
ARCHITECT/ENGINEER INVOICE
To: | University of Florida Planning Design & Construction PO Box 115050 Gainesville, FL 32611-5050 |  | Invoice Number: |  | 0
|  |  |  | Page: | 1 of 1 Pages
|  |  |  | Date: | mmmm dd, yyyy
From: | Firm Name |  |  | Purchase Order # | 0
| Street Address |  |  | UF Project Number:
| City, ST 00000 |  |  | Project Name: | Project Name
SERVICE |  | FEE | % COMP | AMOUNT DUE | LESS PREVIOUSLY BILLED | AMOUNT DUE THIS INVOICE
Pre-Design (PD) |  | 0 |  | 0 | 0 | 0
Concept Schematic Design (CSD) |  | 0 |  | 0 | 0 | 0
Advanced Schematic Design (ASD) |  | 0 |  | 0 | 0 | 0
Design Development (DD) |  | 0 |  | 0 | 0 | 0
60% Construction Documents (GMP CD) |  | 0 |  | 0 | 0 | 0
100% Construction Documents (100% CD) |  | 0 |  | 0 | 0 | 0
Corrected/Conformance Documents |  | 0 |  | 0 | 0 | 0
Bidding or Negotiation Phase |  | 0 |  | 0 | 0 | 0
Construction Administration (CA) |  | 0 |  | 0 | 0 | 0
Substantial Completion |  | 0 |  | 0 | 0 | 0
Final Completion |  | 0 |  | 0 | 0 | 0
Post Occupancy Inspection & Report |  | 0 |  | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 0
ASA-00 (describe service) |  | 0 |  | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 0
GRAND TOTALS |  | 0 |  | 0 | 0 | 0
|  |  |  | Total Due Architect/Engineer |  | 0
CERTIFIED TRUE AND CORRECT BY: |  |  |  | SUPPORTING DOCUMENTS FOR INVOICES (A/E Initial):
Activation Letter of phase being invoiced
Verify current Design Status Report
Verify current Construction Status Report
Approved Contractor Pay Certification
Signature & Typed Name of Principal |  | Date |  | Additional Service Authorizations
INVOICING INSTRUCTIONS: Please prepare invoices properly to avoid delaying payment. For complete instructions, consult the UF Design Services Guide. Invoice using this standard form, and number consecutively starting with "1." Submit signed original (attach appropriate back-up documents to the invoices). Consultant's invoice(s) should be marked "Approved" and signed on the face by a principal of the A/E firm.
PDC Revised: May 2017
Note on F35: Note: Required for design phases only.
Note on F36: Note: Required for all phases of design service. Verify that up to date report has been provided to the Owner.
Note on F37: Note: Required for construction administration phase
Note on F38: Note: Copy of the Owner approved Pay Certification is required for payment under Construction Administration Phase.
Note on F39: Note: Copy of the executed Additional Services Authorization must be attached when billing for that ASA.

## Sample
STANDARD INVOICE FORM
ARCHITECT/ENGINEER INVOICE
To: | University of Florida Facilities Planning & Construction 232 Stadium / PO Box 115050 Gainesville, FL 32611-5050 |  |  | Invoice Number: |  | 7
[5 empty] | Page: | 1 of 1 Pages
[5 empty] | Date: | 2008-10-28
From: | FLW Architects 100 Main Street Usonia, FL 33333 |  |  |  | Purchase Order # | XXXXXXXXXX
[5 empty] | Project Number: | UF-001
[5 empty] | Project Name: | Project Name
SERVICE |  | TOTAL FEE |  | % COMP. | AMOUNT DUE | LESS PREVIOUSLY BILLED | AMOUNT DUE THIS INVOICE
Program Verification |  | 30815 |  | 100% | 30815 | 30815 | 0
Conceptual Schematics |  | 30815 |  | 100% | 30815 | 30815 | 0
Advanced Schematics |  | 46223 |  | 100% | 46223 | 46223 | 0
Design Development |  | 46223 |  | 100% | 46223 | 46223 | 0
50% Construction Documents |  | 15708 |  | 100% | 15708 | 15708 | 0
100% Construction Documents | [6 empty] | 0
Construction Administration |  | 50000 |  | 38% | 19000 | 12500 | 6500
ASA-01(describe service) |  | 4200 |  | 100% | 4200 | 4200 | 0
ASA-02 (describe service) |  | 9800 |  | 100% | 9800 | 9800 | 0
ASA-03 (describe service) |  | 2500 |  | 100% | 2500 | 2500 | 0
ASA-04 (describe service) |  | 90000 |  | 9% | 8100 | 0 | 8100
ASA-05 (describe service) |  | 14020 |  | 0% | 0 | 0 | 0
ASA-06 (describe service) |  | 8000 |  | 42% | 3360 | 2100 | 1260
GRAND TOTALS |  | 348304 |  |  | 216744 | 200884 | 15860
[5 empty] | Total Due Architect/Engineer |  | 15860
CERTIFIED TRUE AND CORRECT BY: |  |  |  |  | SUPPORTING DOCUMENTS FOR A/E INVOICES (A/E Initial):
F. L. Wright |  |  |  |  | Activation Letter of phase being invoiced |  | FLW
[5 empty] | Verify current Design Status Report |  | FLW
[5 empty] | Verify current Construction Status Report |  | FLW
F. L. Wright, President |  |  | 2008-10-30 |  | Approved Contractor Pay Certification |  | FLW
Signature & Typed Name of Principal |  |  | Date |  | Additional Service Authorizations |  | FLW
INVOICING INSTRUCTIONS: Please prepare invoices properly to avoid delaying payment. For complete instructions, consult the UF Design Services Guide. Invoice using this standard form, and number consecutively starting with "1." Submit signed original (attach appropriate back-up documents to the invoices). Consultant's invoice(s) should be marked "Approved" and signed on the face by a principal of the A/E firm.
Note on F30: Note: Required for design phases only.
Note on F31: Note: Required for all phases of design service. Verify that up to date report has been provided to the Owner.
Note on F32: Note: Required for construction administration phase
Note on F33: Note: Copy of the Owner approved Pay Certification is required for payment under Construction Administration Phase.
Note on F34: Note: Copy of the executed Additional Services Authorization must be attached, if payment is desired.