## AE Invoice
STANDARD INVOICE FORM
DESIGN/BUILDER (D/B) DESIGN SERVICES INVOICE
To: | University of Florida Facilities Planning & Construction 232 Stadium / PO Box 115050 Gainesville, FL 32611-5050 |  |  | Invoice Number: |  | 0
[5 empty] | Page: | 1 of 1 Pages
[5 empty] | Date: | mmmm dd, yyyy
From: | Firm Name |  |  |  | Federal ID: | 0
| Street Address |  |  |  | Project Number: | UF-000
| City, ST 00000 |  |  |  | Project Name: | Project Name
SERVICE |  |  | FEE | % COMP | AMOUNT DUE | LESS PREVIOUSLY BILLED | AMOUNT DUE THIS INVOICE
Pre-Design (PD) |  |  | 0 | 25% | 0 | 0 | 0
Concept Schematic Design (CSD) |  |  | 0 |  | 0 | 0 | 0
Advanced Schematic Design (ASD) |  |  | 0 |  | 0 | 0 | 0
Design Development (DD) |  |  | 0 |  | 0 | 0 | 0
60% Construction Documents (GMP CD) |  |  | 0 |  | 0 | 0 | 0
100% Construction Documents (100% CD) |  |  | 0 |  | 0 | 0 | 0
Corrected/Conformance Documents |  |  | 0 |  | 0 | 0 | 0
Bidding or Negotiation Phase |  |  | 0 |  | 0 | 0 | 0
Construction Administration (CA) |  |  | 0 |  | 0 | 0 | 0
Substantial Completion |  |  | 0 |  | 0 | 0 | 0
Final Completion |  |  | 0 |  | 0 | 0 | 0
Post Occupancy Inspection & Report |  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
ASA-00 (describe service) |  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
GRAND TOTALS |  |  | 0 |  | 0 | 0 | 0
[5 empty] | Total Due Design/Builder |  | 0
CERTIFIED TRUE AND CORRECT BY: |  |  |  |  | SUPPORTING DOCUMENTS FOR INVOICES (D/B Initial):
Activation Letter of phase being invoiced
Verify current Design Status Report
Verify current Construction Status Report
Approved Contractor Pay Certification
Signature & Typed Name of Principal |  |  | Date |  | Additional Service Authorizations
UNIVERSITY APPROVAL |  | Date | Signature |  | INVOICING INSTRUCTIONS: Please prepare invoices properly to avoid delaying payment. For complete instructions, consult the UF Design Services Guide. Invoice using this standard form, and number consecutively starting with "1." Submit signed original (attach appropriate back-up documents to the invoices). Consultant's invoice(s) should be marked "Approved" and signed on the face by a principal of the D/B firm.
Date Received (FPC Project Manager):
Services Rendered as Invoiced (FPC Project Manager):
Invoice Consistent with Contract (FPC Contract Administrator):
Invoice Approved (FPC Asst VP):
FPC Revised: August 2008
Note on A42: Note: By Project Manager
Note on A44: Note: By Business Manager
Note on A43: Note: By Project Manager
Note on F38: Note: Copy of the Owner approved Pay Certification is required for payment under Construction Administration Phase.
Note on F39: Note: Copy of the executed Additional Services Authorization must be attached when billing for that ASA.
Note on F36: Note: Required for all phases of design service. Verify that up to date report has been provided to the Owner.
Note on F37: Note: Required for construction administration phase
Note on F35: Note: Required for design phases only.
Note on A45: Note: By Business Manager

## Sample
STANDARD INVOICE FORM
DESIGN/BUILDER (D/B) DESIGN SERVICES INVOICE
To: | University of Florida Facilities Planning & Construction 232 Stadium / PO Box 115050 Gainesville, FL 32611-5050 |  |  | Invoice Number: |  | 7
[5 empty] | Page: | 1 of 1 Pages
[5 empty] | Date: | 2008-10-28
From: | FLW Architects 100 Main Street Usonia, FL 33333 |  |  |  | Federal ID: | XX XXXXX
[5 empty] | Project Number: | UF-001
[5 empty] | Project Name: | Project Name
SERVICE |  | TOTAL FEE |  | % COMP. | AMOUNT DUE | LESS PREVIOUSLY BILLED | AMOUNT DUE THIS INVOICE
Program Verification |  | 30815 |  | 100% | 30815 | 30815 | 0
Conceptual Schematics |  | 30815 |  | 100% | 30815 | 30815 | 0
Advanced Schematics |  | 46223 |  | 100% | 46223 | 46223 | 0
Design Development |  | 46223 |  | 100% | 46223 | 46223 | 0
50% Construction Documents |  | 15708 |  | 100% | 15708 | 15708 | 0
100% Construction Documents | [6 empty] | 0
Construction Administration |  | 50000 |  | 38% | 19000 | 12500 | 6500
ASA-01(describe service) |  | 4200 |  | 100% | 4200 | 4200 | 0
ASA-02 (describe service) |  | 9800 |  | 100% | 9800 | 9800 | 0
ASA-03 (describe service) |  | 2500 |  | 100% | 2500 | 2500 | 0
ASA-04 (describe service) |  | 90000 |  | 9% | 8100 | 0 | 8100
ASA-05 (describe service) |  | 14020 |  | 0% | 0 | 0 | 0
ASA-06 (describe service) |  | 8000 |  | 42% | 3360 | 2100 | 1260
GRAND TOTALS |  | 348304 |  |  | 216744 | 200884 | 15860
[5 empty] | Total Due Design/Builder |  | 15860
CERTIFIED TRUE AND CORRECT BY: |  |  |  |  | SUPPORTING DOCUMENTS FOR INVOICES (D/B Initial):
F. L. Wright |  |  |  |  | Activation Letter of phase being invoiced |  | FLW
[5 empty] | Verify current Design Status Report |  | FLW
[5 empty] | Verify current Construction Status Report |  | FLW
F. L. Wright, President |  |  | 2008-10-30 |  | Approved Contractor Pay Certification |  | FLW
Signature & Typed Name of Principal |  |  | Date |  | Additional Service Authorizations |  | FLW
UNIVERSITY APPROVAL |  | Date | Signature |  | INVOICING INSTRUCTIONS: Please prepare invoices properly to avoid delaying payment. For complete instructions, consult the UF Design Services Guide. Invoice using this standard form, and number consecutively starting with "1." Submit signed original (attach appropriate back-up documents to the invoices). Consultant's invoice(s) should be marked "Approved" and signed on the face by a principal of the D/B firm.
Date Received (FPC Project Manager):
Services Rendered as Invoiced (FPC Project Manager):
Invoice Consistent with Contract (FPC Contract Administrator):
Invoice Approved (FPC Asst VP):
Note on A37: Note: By Project Manager
Note on A39: Note: By Business Manager
Note on A38: Note: By Project Manager
Note on F33: Note: Copy of the Owner approved Pay Certification is required for payment under Construction Administration Phase.
Note on F34: Note: Copy of the executed Additional Services Authorization must be attached, if payment is desired.
Note on F31: Note: Required for all phases of design service. Verify that up to date report has been provided to the Owner.
Note on F32: Note: Required for construction administration phase
Note on F30: Note: Required for design phases only.
Note on A40: Note: By Business Manager