## Cert Part Pay
|  |  | PDC Use Only |  | Date Received:
Corrected Date Received:
Date Uploaded to UF Marketplace:
UNIVERSITY OF FLORIDA
PLANNING DESIGN AND CONSTRUCTION
CONTRACTORS APPLICATION AND CERTIFICATION OF PARTIAL PAYMENT
Contractor: | Add Contractor Name on SOV |  | Application No.: | 1 | Enter Number in SOV | Notes
Address: |  | Page: |  |  | 1 of 1 Pages
|  | Date: |  |  | 2023-07-01
PO # | 2024#### | NTP Date: |  |  | 2023-06-01
UF Project No: | Enter Number in SOV | No. of Days Elapsed: |  |  | 59
Project Name: | Add Project Name on SOV | Previous Pay Period Ending: |  |  | 2023-06-30
|  | This Pay Period Ending: |  |  | 2023-07-30
| Reference Schedule of Values |  | No. of Days |  | Progress Payment Calculation* | Contract Accounting
C | ORIGINAL CONTRACT (Sum / Days) |  | 100 |  | 0 | 0
C | Net Amount of CHANGE ORDERS | Scope of Work | 0 |  | 0 | 0
C | Net Amount of CHANGE ORDERS | Owner Direct Purchase |  |  |  | 0
C | CURRENT CONTRACT (Sum / Days) |  | 100 |  | 0 | 0
H | BALANCE TO FINISH (Sum / Days) |  | 41 |  |  | #DIV/0!
D | COMPLETED TO DATE (Previous G) | From Previous Cert. |  |  | 0 | 0
E | COMPLETED TO DATE | From This Cert. |  |  | #DIV/0! | #DIV/0!
F | MATERIALS STORED |  |  |  | 0 | 0
|  | Owner Direct Purchase |  |  | 0
G | TOTAL COMPLETED & STORED |  |  |  | #DIV/0! | #DIV/0!
I | LESS RETAINAGE | Minimum 5% |  |  |  | #DIV/0!
I | LESS RETAINAGE | Exceptions |  |  |  | 0
I | LESS RETAINAGE | Previous |  |  |  | 0
| TOTAL |  |  |  |  | #DIV/0!
| LESS PREVIOUS PAYMENTS | Enter Amount Manually |  |  |  | 0
| AMOUNT THIS CERTIFICATE |  |  |  |  | #DIV/0!
| * % completed calculation for progress payments adjusted to reflect ODP Program intended for both Builder Project and Overhead Fee and the A/E Construction Administration Phase services fee. |  |  |  | #DIV/0! | #DIV/0!
CERTIFICATION BY BUILDER: According to the best of my knowledge and belief, I certify that all items and amounts shown on the face of this Application are correct, that all Work has been performed and material supplied in full accordance with the terms and conditions of the Contract, and that all just and lawful bills against me and my Subcontractors for labor and equipment employed in the performance of this Contract have been paid in full in accordance with the terms and conditions. I further certify that all Subcontractors providing service for the Work are licensed according to the requirements of the State of Florida.
| Date: |  | Contractor:
| State of _______, County of ________ |  | Subscribed and sworn before me this ___ day of ______, 20___.
| Notary Public: |  | Commissions Expires:
CERTIFICATION OF ARCHITECT/ENGINEER: I certify that I have checked and verified this Progress Payment Application; that to the best of my knowledge and belief the above application is a true statement of the value of the Work performed and the materials suitably stored on the site; and that the Work and materials included in this Certificate has been formed and materials supplied in accordance with the requirements of the Construction Documents and this Contract, and I approve for payment the Builder's certified amount noted above.
| Date: |  | Architect/Engineer
Updated March 2024

## CO Summary
UNIVERSITY OF FLORIDA |  |  |  | PLANNING DESIGN AND CONSTRUCTION
CHANGE ORDER SUMMARY
Application No.: | 1 | [5 empty] | Date: | 2023-07-01
UF Project No: | Enter Number in SOV | [5 empty] | Contractor: | Add Contractor Name on SOV
Change Orders Approved to Date |  | Scope of Work |  |  | Owner Direct Purchase |  | CM Contingency |  | Bid Package Savings
Change Order No. | Description | No. of Days | Additions | Deductions |  | ODP Tax Savings | Additions | Deductions | Additions | Deductions
CO-00 | Builder Contingency Value from the GMP-01** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-Total |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
| Net Amount of Change Orders | 0 | 0 |  | 0 | 0 | 0 |  | 0
* All change order numbers shall be used consecutively and only once. Builder shall prepare change orders for all ODPs, trade buyouts and approved transfers. **Add another line for any future GMPs
THIS FORM MUST EQUAL THE NUMBERS ON THE SCHEDULE OF CONTRACT VALUES.
PLEASE ENTER DEDUCTIONS AS NEGATIVE AMOUNTS.

## Phased Summary
UNIVERSITY OF FLORIDA |  |  |  | PLANNING DESIGN AND CONSTRUCTION
PHASED CONSTRUCTION SUMMARY
Application No.: | 1 |  |  | Date: | 2023-07-01
UF Project No: | Enter Number in SOV |  |  | Contractor: | Add Contractor Name on SOV
Change Orders Approved to Date |  | No. of Days | Cost of Work | CM Contingency | Staffing Cost | Overhead & Profit | General Conditions | ERP/GMP Total
ERP/GMP No. | Description
ERP/GMP 1 | Description of ERP/GMP | 0 | 0 | 0 | 0 | 0 | 0 | 0
ERP/GMP 2 | Description of ERP/GMP | 0 | 0 | 0 | 0 | 0 | 0 | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
ERP/GMP No. |  | 0 | 0 | 0 | 0 | 0 |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Amount Shown in GMP Scheduled Value |  |  | 0 | 0 | 0 | 0 | 0 | 0
THIS FORM MUST EQUAL THE GMP SCHEDULED VALUE

## Sched Value
UNIVERSITY OF FLORIDA | [10 empty] | PLANNING, DESIGN AND CONSTRUCTION
SCHEDULE OF CONTRACT VALUES
| Invoice Number: | 1 | [6 empty] | 2024#### |  |  |  | Date: | 2023-07-01
| PDC Project Number: | Enter Number in SOV | Project Name: | Add Project Name on SOV |  |  |  | PO Number |  |  |  |  | Contractor: | Add Contractor Name on SOV
A | B | [7 empty] | D | E | F | G |  | H | I
ITEM NO. (Builder's Cost Codes) | DESCRIPTION OF WORK Trade Contractor Name & Scope of Work | [7 empty] | WORK COMPLETED |  | MATERIALS | Total Completed & Stored to Date | % Complete | Balance to Finish | RETAINAGE
|  | GMP Scheduled Value | CHANGE ORDERS |  |  |  |  | Subcontractor Total Contract Amount & Allowances | Amount from Previous Month Pay Application | This Period | This Period Presently Stored |  |  |  | Minimum 5% | Amount from Previous Month Retainage | This Period Retainage | Final Conditional Release of Lien (CROL) Pay App # Received
|  |  | Contract Change | Owner Direct Purchase | ODP Tax Savings | Bid Package Savings/Loss | Builder Contingency
Construction
1A | General
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
2B | Demolition
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
3A | Trade Package
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
4A | Trade Package
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
5A | Trade Package
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
6D | General Trade
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
7B | Trade Package
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
8D | Door/Hardware
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
9A | GB Assembly
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
9B | Flooring
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
9C | Acoustics
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
9D | Painting
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
10A | Specialization
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
15A | HVAC
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
15C | Fire Protection
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
16A | Electrical
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
17A | Trade Package
| Subcontractor Name | 0 | 0 | 0 | 0 | 0 | 0
| CO # + (COP#, ODP#, Transfer, BO) | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | Pay App #
Final Pay | Transfer of Balance to Owner
| Allowances - CO# | 0 | 0 | 0 | 0 | 0 | 0
| Bid Savings - CO# | 0 | 0 | 0 | 0 | 0 | 0
| Tax Savings - CO# | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total - Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
4.2.5 CM 7.4.5 D/B 5.2 D/B/B | Builder Contingency | 0 |  |  |  |  | 0 | 0
| Add / Credit |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
| Subtotal Builder Contingency | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
4.2.2 CM 7.4.2 D/B 5.2 D/B/B | Builder Staffing Costs | 0 | [5 empty] | 0
| Add / Credit |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
| Subtotal Builder Staffing Costs | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 | 0
4.2.3a CM 7.4.3a D/B 5.2a D/B/B | Builder General Conditions (Lump Sum) | 0 | [5 empty] | 0
| Add / Credit |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
| Subtotal Builder GCs (Lump Sum ) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 | 0
4.2.3b CM 7.2.3b D/B 5.2b D/B/B | Builder General Conditions (Actual Expenditures excl. bond, insurance, permit, pre-con fees) | 0 | [5 empty] | 0 | [10 empty] | For Majors, remove the Pre-Con and permit Fees from this line.
| Add / Credit |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
| Subtotal Builder GCs (Actual Expenditures excl. Bond, Insurances, Permit, Pre-Con fees) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 | 0
| Total Construction, Builder Contingency, Staffing & General Conditions (LS & Actual Exp. excl. Bond, Insurances, Permit, Pre-Con Fees) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
4.2.4 CM 7.4.4 D/B 5.2 D/B/B | Builder Overhead & Profit | 0 | [5 empty] | 0
| Add / Credit |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
| Subtotal Builder Profit & Overhead | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0
4.2.3c CM 7.4.3c D/B 5.2c D/B/B | Builder General Conditions (Bond, Insurances, Permit, Pre-Con Fees) | 0 | [5 empty] | 0 | [10 empty] | For Majors, remove the Pre-Con and permit Fees from this line.
| Add / Credit |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0
| Subtotal Builder GCs (Bond, Insurances, Permit, Pre-Con Fees) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 | 0
| Total GMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0
| Final Pay Application Preparation for Reimbursables | [8 empty] | This Pay Application: |  | #DIV/0!
| 1. Return Remaining Allowances | 0
| 2. Return Remaining Bid Savings | 0
| 3. Return Remaining Tax savings | 0 | [7 empty] | CA Notes:
| 4. Return Remaining Builder Contigency | 0 | Enter Manually
| 5. Return Remaining Staffing | 0 | Enter Manually
| 6. Return Remaining General Cond | 0 | Enter Manually
| 7. Sub Total | 0
| 8. Actual Percentage of OH&P | 0% | Enter Manually
| 9. Return OH&P based on #7 above | 0

## Staffing Costs
UNIVERSITY OF FLORIDA | [9 empty] | PLANNING DESIGN AND CONSTRUCTION
SCHEDULE OF CONTRACT VALUES - STAFFING COSTS (ARTICLE 4.2.2 CM, 7.4.2 D/B, & 5.2 D/B/B)
| Invoice Number: | 1 | [7 empty] | Date: |  | 2023-07-01
| PDC Project No: | Enter Number in SOV | [7 empty] | Contractor: |  | Add Contractor Name on SOV
A | B | C | [7 empty] | D
ITEM NO. | DESCRIPTION OF WORK | QUANTITY |  | UNIT COST |  | ORIGINAL GMP AMOUNT | CHANGE ORDERS | BUILDER CONTINGENCY | CURRENT |  | COSTS
|  | TOTAL | UNITS | LABOR | BURDEN | [5 empty] | TO DATE | PRIOR | THIS PERIOD | REMAINING
Project Personnel
CM 4.2.2(i) D/B 7.4.2(i) D/B/B 5.2 | Field employees | Approved GMP Staffing Value: |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| Project Manager Name | 0 | Hrs | [6 empty] | Monthly Lump Sum Costs to be billed per month (Staffing Cost/# of Months) |  |  | 0
| General Superintendent Name | 0 | Hrs
| Assistant Superintendent Name | 0 | Hrs
| MEP Superintendent Name | 0 | Hrs
| Safety Engineer Name | 0 | Hrs
| Project Engineer Name | 0 | Hrs
| Administrative Assistant Name | 0 | Hrs
Other
| Sub-Total Project Site Personnel This Period | [7 empty] | 0 |  | 0 | 0 | 0 | 0
| Project Site Cost |  |  | AMOUNT
CM 4.2.2(iii) D/B 7.4.2(iii) D/B/B 5.2 | Direct Costs Not in GCs | Approved Vehicle Costs Value:
| Job Site Const Vehicles Includes fuel/repairs/maint and related |  | Months |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub-Total Project Site Costs | [7 empty] | 0 |  | 0 | 0 | 0 | 0
Note: | Adjustments to the Schedule of Values allowances under CM Article 4.2.2, D/B Article 7.4.2, and D/B/B Article 5.2 are permitted only when documented through the Change Order process.
CERTIFICATION BY BUILDER: According to the best of my knowledge and belief, I certify that all field employees’ hours shown during this pay period are a true and accurate reflection of the hours worked.
| Date: |  |  | Contractor:
| State of _______, County of ______________________________ |  |  | Subscribed and sworn before me this ___ day of ______, 20___.
| Notary Public: |  |  | Commissions Expires:

## General Conditions Cost
UNIVERSITY OF FLORIDA | [11 empty] | PLANNING DESIGN AND CONSTRUCTION
SCHEDULE OF CONTRACT VALUES - GENERAL CONDITIONS COST (ARTICLE 4.2.3 CM, 7.4.3 D/B, & 5.2 D/B/B)
| Invoice Number: | 1 | [9 empty] | Date: |  | 2023-07-01
| PDC Project No.: | Enter Number in SOV | [9 empty] | Contractor: |  | Add Contractor Name on SOV
A | B | C | [9 empty] | D
ITEM NO. | DESCRIPTION OF WORK | QUANTITY |  | UNIT | COST | ORIGINAL GMP | CHANGE ORDERS | ODP TAX SAVINGS | BID PACKAGE SAVINGS | BUILDER CONTINGENCY | CURRENT |  | COSTS
|  | TOTAL | UNITS | LABOR | MATERIAL |  |  | SAVINGS | SAVINGS |  |  |  | TO DATE | PRIOR | THIS PERIOD | REMAINING
Lump Sum
4.2.3a CM 7.4.3a D/B 5.2a D/B/B | General Conditions (LS)
| General Conditions (LS) | 1 | LS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Job Site Const Vehicles Includes fuel/repairs/maint and related (MINOR PROJECTS ONLY) | 0 | LS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| TOTAL- GENERAL CONDITIONS LS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Actual Expenditures
4.2.3b CM 7.4.3b D/B 5.2b D/B/B | General Conditions Actual Expenditures (excl. Bond, Insurances, Permit, Pre-con fees)
| Heavy Equipment Rental | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Scaffolding Rental | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Survey/Tests | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Material Testing | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Final Cleaning | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| MOT/Flagmen | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| New Building Utilities (if required) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Swing Space Rental | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Other Approved Costs | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Other Approved Costs | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| TOTAL- GENERAL CONDITIONS ACTUAL EXPENDITURES (excl. Bond, Insurances, Permit, Pre-Con Fees) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
4.2.3c CM 4.2.3c D/B 5.2c D/B/B | General Conditions (Bond, Insurances, Permit, Pre-con fees)
| Builder's risk insurance | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Payment & Performance bonds | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| General Liability Insurance | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Building & Permit fee | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Pre-Con Fees | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| TOTAL- GENERAL CONDITIONS (Bond, Insurances, Permit, Pre-Con Fees) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| TOTAL- GENERAL CONDITIONS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Note: | Adjustments to the Schedule of Values allowances under CM Article 4.2.3, D/B Article 7.4.3, and D/B/B Article 5.2 are permitted only when documented through the Change Order process.

## Inventory (hidden)
UNIVERSITY OF FLORIDA |  |  | PLANNING DESIGN AND CONSTRUCTION
PROJECT FUNDED FURNITURE AND EQUIPMENT INVENTORY
*Items purchased under Article 4.2(b) using project funds are to be inventoried at each Pay Application and surveyed and returned to the Owner at completion of the project.
Payment Application No.: | 1 |  |  |  |  | Date: | 2023-07-01
UF Project Number: | Enter Number in SOV |  |  |  |  | Contractor: | Add Contractor Name on SOV
Description |  | Serial No. (or other ID) | Date Purchased | Paid under Pay. App. No. | Sched. of Values Item No. | Quantity | Unit Price | Sub-Total Amount | Comments
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | Total | 0
Submitted by: |  |  | Inventory surveyed or returned to the Owner: (Signed on Final Certificate of Partial Payment) |  |  |  | Inventory surveyed or returned to the Owner: (Signed on Final Certificate of Partial Payment)
Contractor |  |  | PDC Project Manager* |  |  |  | PDC Contract Administrator*

## SBR
UNIVERSITY OF FLORIDA |  |  | SMALL BUSINESS RELATIONS
BUILDER’S SMALL AND MINORITY BUSINESS ENTERPRISE PAYMENT STATUS REPORT FORM
| SUPPLEMENT TO CONTRACTOR’S PARTIAL PAYMENT REQUEST |  |  |  |  | Pay Application No.: | 1
SUPPLEMENT TO CONTRACTOR’S FINAL PAYMENT REQUEST
Construction Manager: | [5 empty] | Date: | 2023-07-01
UF Project Name |  | Add Project Name on SOV
UF Project No. |  | Enter Number in SOV
Name of CSMBE Firm (Certified by the State of Florida’s Office of Supplier Diversity) |  |  | Trade Services or Supplies / Materials Provided by CSMBE* | Original Subcontract Amount | Total amount paid to CSMBE Firm | Unpaid Balance | % Particpation to Date (total amount paid to CSMBE Firm/GMP)
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | 0 | 0 | 0 | #DIV/0!
*CSMBE - Certified Small and Minority Business Enterprises |  |  | Totals | 0 | 0 | 0 | #DIV/0!
| SUBMIT to: | Dwan Courtney, Director dwan@ufl.edu | Small Business Relations 971 Elmore Hall / PO Box 115250 Gainesville, FL 32611-5250 |  | P: (352) 392-0380 www.sbr.admin.ufl.edu
This reports covers Small, HUB Zone, Minority, Small Disadvantaged, Veteran, Service-Disable Veteran and Women-Owned Businesses.
This report is for both Major and Minor projects.

## Checklist
www.facilities.ufl.edu
BUSINESS AFFAIRS |  |  |  | PLANNING DESIGN AND CONSTRUCTION
BUILDER PAY APPLICATION (CONSTRUCTION PHASE) CHECKLIST
Project Name: | Add Project Name on SOV |  |  | Project Number: | Enter Number in SOV
Invoice Number: | 1 |  |  | Date: | 2023-07-01
DESCRIPTION |  | PM | CA | NOTES
First Pay Application:
Compare with an initial Schedule of Values with the Construction Authorization values to ensure that each major cost category (Cost of the Work, Staffing, General Conditions, OH&P, Bonds & Insurance) matches.
Compare Schedule of Values - Direct Costs (subcontractors) - with Guaranteed Maximum Price Proposal to confirm correlation between documents
Review Schedule of Values – Staffing and General Conditions (indirect cost) – and compare each line item to the negotiated estimates or allowances in the Guaranteed Maximum Price (GMP) Proposal
Check dates for all incurred costs against date of the Notice To Proceed (NTP) letter – costs incurred prior to the NTP are not reimbursable as a construction cost, except those authrized by the PM
All pay applications:
Confirm that certificate was signed
Confirm receipt of electronic monthly report. This report must be filed in BIM360 according to filing guidelines.
Compare "Scheduled Values" column with the rows and columns of the Approved GMP Authorization to ensure all values match precisely.
Compare with an initial Schedule of Values (Total Contract Amount and Allowances) column match precisely with the executed contracts for each bid package to ensure proper “original” amounts are captured.
Confirm with and initial per line that trade packages for all subcontractors listed in Schedule of Values ( direct cost) have been captured fiscally via a Change Order
Confirm that bid savings (+/-) for all new trade packages is added to Schedule of Values (direct cost)
Confirm with an initial accuracy of percent-complete estimates for each subcontractor’s work (i.e. do you agree that the in-place masonry is 35% complete?) and discuss or resolve as needed with Builder. A/E shall confirm the same.
Confirm that Owner Direct Purchase (ODP) tax savings is added to Schedule of Values (direct cost)
Confirm that ODP Change Order(s) to capture monies for deleted materials are pending or in-process
Confirm that all Change Order(s) (+/-) and their respective Change Order Proposals (COP) being billed are added to Schedule of Values
Confirm that all Change Order(s) (+/-) and their respective Change Order Proposals (COP) added to the SOV are approved by all parties.
Check retainage to ensure that proper retainage is withheld for all direct and indirect costs - currently at 5%.
Confirm with an initial retainage exceptions, if applicable
Confirm that all “From Previous Certificate” column amounts in the Schedule of Values match to the prior pay application | Confirm that all “From Previous Certificate” column amounts in the Schedule of Values match to the prior pay application
Check “This Period” billing for each subcontractor against Subcontractor’s invoice to confirm that billing is equal to the amount billed by the subcontractor in their SOV back up | Check “This Period” billing for each subcontractor against Subcontractor’s invoice to confirm that billing is equal to or less than amount billed by subcontractor
Review “Presently Stored” column and confirm that materials stored offsite have required documentation (photos and insurance) included in this pay applicaton | Review “Presently Stored” column and confirm that materials stored offsite have required documentation (photos and insurance)
For all Staffing Costs and General Conditions allowable by Contract, review supporting documentation such as time sheets for all approved staff and % allocation of time billed per contract. | For all Staffing Costs and General Conditions allowable by Contract, review supporting documentation for completeness, mathematical accuracy, and reasonableness
For all Staffing Costs and General Conditions, confirm that no duplicated invoices previously paid with a prior pay application are included in current pay application | For all Staffing Costs and General Conditions, confirm that no duplicated invoices previously paid with a prior pay application are included in current pay application
For all Staffing Costs and General Conditions, review supporting documents to assure that no mark-up, interest, late payment fees, etc. are included in expenditures | For all Staffing Costs and General Conditions, review supporting documents to assure that no mark-up, interest, late payment fees, etc. are included in expenditures
Verify that the “Progress payment calculation” that accounts for ODP contract reductions is correct | Verify that the “Progress payment calculation” that accounts for ODP contract reductions is correct
Confirm that all project-funded assets (to be turned over to Owner at end of project) are included on the Project Funded Furniture and Equipment Inventory Report | Confirm that all project-funded assets (to be turned over to Owner at end of project) are included on the Project Funded Furniture and Equipment Inventory Report
Confirm that small and minority business firms are added to the Minority Business Enterprise Payment Status Report | Confirm that small and minority business firms are added to the Minority Business Enterprise Payment Status Report
Spot-Check all back up documentation for the GC re-imbursables documentation for completeness, mathematical accuracy, and reasonableness | Spot-check all documentation for completeness, mathematical accuracy, and reasonableness
Write new and review comments & discrepancies from previous pay application(s) for resolution, correction, etc. It is acceptable to postpone making changes of minor issues to the next pay application with a note comment on the application | Review comments & discrepancies from previous pay application(s) for resolution, correction, etc.
Closeout: | Closeout:
Confirm permanent Certificate of occupancy is in place | Perform reconciliation on Owner Direct Purchases
Perform reconciliation and confirm associated change order on Owner Direct Purchases | Perform reconciliation on Owner Direct Purchases
Confirm that closeout change Order(s) was executed and included in this final pay application | Confirm that closeout change Order(s) was executed
Confirm all punchlist issues have been resolved, inspected and accepted | Confirm that all Substantial Completion (SC) and Final Completion (FC) deliverables and project-funded furniture & equipment (F&E) have been received
Confirm that all Substantial Completion (SC) and Final Completion (FC) deliverables and project-funded furniture & equipment (F&E) have been received and documented | Confirm that all Substantial Completion (SC) and Final Completion (FC) deliverables and project-funded furniture & equipment (F&E) have been received
Confirm that conditional or final releases of lien have been received for each of the line items on the SOV | Confirm that releases of lien have been received
Confirm that all LEED documentation submittals have been provided and are complete | Confirm that releases of lien have been received
Confirm Elevator Certificates have been received and documented | Confirm that releases of lien have been received
Confirm that final approved TAB report has been received and files | Confirm that releases of lien have been received
Confirm that all videos for UG and all Training videos have been received | Confirm that releases of lien have been received
Confirm that all keys (master/slave) borrowed have been returned | Confirm that releases of lien have been received
Confirm all one year warranty letters have been received and documented | Confirm that releases of lien have been received
Confirm that all red lined documents and as-builts Revit Model have been received and documented - PDF Format | Confirm that releases of lien have been received
Confirm no outstanding invoices remain with Facilities Services Accounting for unpaid Utilities | Confirm that releases of lien have been received
Confirm reconciliation of Builder's insurance and bond final costs for any refunds to Owner | Confirm that releases of lien have been received
Confirm receipt of Asset Spreadsheet for PO&M | Confirm that releases of lien have been received

## Compatablity (hidden)
Compatibility Report for ContractorPayApp for New Contract.xls
Run on 5/12/2008 13:46
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
| Minor loss of fidelity | # of occurrences
| Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 67